## Summary
DataFlow live QE — 2026-10-04
Target: https://www.datawrap.io workspace via MCP. Sample row values are not stored in this workbook.
Status | Cases
Pass | 47
Fail | 17
Blocked | 4
In Progress | 0
What was fixed in this change | 68
1. Dataset lookup binds the uploaded file. Production still returns the Financial Services template for sample_payments until deploy (TC-054).
2. Contract census uses count_contracts_by_status when the brief page is full. list_contracts returns total, truncated, and by_status. Production still returns the page length until deploy.
3. list_jobs defaults to scope=workspace, the same population as the brief. scope=all is explicit. Production still returns 575 with no scope field (TC-040).
4. confirm_action spends the same ack as Confirm. It is not on the deployed server (TC-051). A call with no request returns an error and does not mutate (TC-049).
5. Workspace API keys store a role. A key with no role resolves to editor, so MCP can create connectors, transfers, and schedules. Unknown labels resolve to viewer.
6. MCP client snippets use the absolute tenant URL and a Bearer header. They do not point at api.datawrap.io or an unpublished bridge package.
Not changed: the 10 connector dial failures (TC-052), no schedule was created, and no new transfer was written to PostgresVenkat. CDC remains at-least-once upsert.
7. start_dataset_transfer stages an uploaded file into a saved connector. Confirm keeps kind=file and refuses a path outside the upload directory. Measured on a payments.csv fixture, not on PostgresVenkat.
8. confirm_action was run through copilot_confirm for a connector, an enabled schedule, a schedule run, and a file transfer. Replay returns the first result. A viewer refusal and a path outside the upload tree leave the ack spendable. 7 passed in tests/test_mcp_confirm_route.py. sample_payments.csv is the 10-row fixture. Nothing was written to PostgresVenkat.
9. MCP can create a SQLite connector from a file path. Streamable POST /api/v1/mcp loaded sample_payments.csv (10 rows) into that file, scheduled the table onto a second SQLite file, and ran the schedule. Both tables counted 10. Replay did not insert again. tests/test_mcp_sqlite_file_transfer.py passed. The probe and the draft share sqlite_file_path.
10. File columns the parser did not type are not declared TEXT. JSONL sample_mixed_types is refused until source_timezone is an IANA zone, then loads 3 rows into SQLite with created_at TIMESTAMPTZ and payload_b64 BLOB. TSV is 3 rows, HR JSON is 5. The HR schedule pauses and deletes through confirm_action. tests/test_mcp_sqlite_file_transfer.py: 2 passed. Nothing was written to PostgresVenkat.

## Test Cases
Case ID | Area | Priority | Test data | Steps | Expected | Actual | Status | Evidence
TC-001 | MCP | P1 | Live https://www.datawrap.io/api/v1/mcp | POST initialize | Server identifies as dataflow and states tools/call needs a Bearer token | serverInfo name=dataflow version=2.0.0, instructions require Bearer | Pass | initialize 200
TC-002 | MCP | P1 | Same endpoint | tools/list | Tool catalog is returned without executing tools | 51 tools including list_connectors, plan_transfer, start_transfer, map_connector_schemas | Pass | tools/list 200
TC-003 | MCP | P1 | No Authorization header | tools/call list_connectors | Tool execution is refused | JSON-RPC -32001 Authentication required | Pass | unauthenticated call
TC-004 | MCP | P1 | Workspace API key | tools/call describe_pilot | Authenticated tool runs | isError false, role Datawrap Pilot, CDC described as confirm-gated | Pass | describe_pilot
TC-005 | MCP | P1 | Workspace API key | tools/call brief_workspace | Counts come from live stores | 11 connectors, job_count 544, contract_count 50, schedule_count 0 | Fail | See TC-040 and TC-041. Brief under-counts contracts and does not match the job census.
TC-006 | Connectors | P1 | Saved connector SnowFlake | test_connector | Connection succeeds or returns the driver error | last_test_ok false. Snowflake connection failed (account, warehouse, database, schema, role) | Fail | Environment. Not a code defect. Last prior test 2026-09-20.
TC-007 | Connectors | P1 | SnowFlake Dest | test_connector | Connection succeeds or returns the driver error | last_test_ok false. Same Snowflake failure class | Fail | Environment
TC-008 | Connectors | P1 | MySQL | test_connector | Connection succeeds or returns the driver error | Lost connection to MySQL server during query | Fail | Environment. Railway proxy closed the session.
TC-009 | Connectors | P1 | PostgreSQL connection | test_connector | Connection succeeds or returns the driver error | Server closed the connection unexpectedly | Fail | Environment
TC-010 | Connectors | P1 | MySQLDest | test_connector | Connection succeeds or returns the driver error | Lost connection to MySQL server during query | Fail | Environment
TC-011 | Connectors | P1 | Redis | test_connector | Connection succeeds or returns the driver error | Connection reset by peer on the saved proxy endpoint | Fail | Environment. List view shows host localhost; the dial target was the saved proxy.
TC-012 | Connectors | P1 | MySQL connectionCrown | test_connector | Connection succeeds or returns the driver error | Lost connection to MySQL server during query | Fail | Environment
TC-013 | Connectors | P1 | PostgresVenkat | test_connector | PostgreSQL connects and reports schema objects | Connected. 10 tables in schema public | Pass | test_connector ~408ms
TC-014 | Connectors | P1 | MySQL venky2001 | test_connector | Connection succeeds or returns the driver error | Lost connection to MySQL server during query | Fail | Environment
TC-015 | Connectors | P1 | Snowflake connection | test_connector | Connection succeeds or returns the driver error | Snowflake connection failed | Fail | Environment
TC-016 | Connectors | P1 | Snowflake_venky | test_connector | Connection succeeds or returns the driver error | Snowflake connection failed | Fail | Environment
TC-017 | Postgres read | P1 | PostgresVenkat | list_connector_objects limit 30 | Live object list, no write | 10 tables: _dataflow_write_ledger, employeedata, jobs, kilo, mm, portfolios, users, users_df_quarantine, were, yours | Pass | connected true, truncated false
TC-018 | Reconcile | P1 | Job 6ac0f355fddf0d6787ee449b excel to kilo | aggregate COUNT on kilo | Destination row count matches the completed job | Job records_processed 10, rejected 0. Live COUNT(*) = 10 exact | Pass | SELECT COUNT(*) FROM kilo
TC-019 | Reconcile | P1 | Job mm completed 5 rows | aggregate COUNT on mm | Destination row count matches the job | Live COUNT(*) = 5 exact | Pass | PostgresVenkat.mm
TC-020 | Reconcile | P1 | Job were completed 5 rows | aggregate COUNT on were | Destination row count matches the job | Live COUNT(*) = 5 exact | Pass | PostgresVenkat.were
TC-021 | Quarantine | P1 | Job 6abec09fd89ff5d3854e8b96 Critical Source to bgg | get_job and confirm dest was not written | Empty phone values are quarantined, not coerced into a NOT NULL integer | status failed, records 0, rejected 3, quarantine 3, class EMPTY_VALUE_NOT_NULLABLE. Table bgg is absent | Pass | Fail-closed. Not a defect to coerce empty phone to a number.
TC-022 | Schema | P1 | PostgresVenkat.kilo | introspect_connector_schema | Column count matches the job mapping count | 13 columns including customer_id, email, phone. Job mappings_count 13 | Pass | introspect
TC-023 | Quarantine | P2 | PostgresVenkat.users_df_quarantine | aggregate COUNT | Quarantine table is readable | COUNT = 130 exact, read_only true | Pass | Row values not copied into this log
TC-024 | Datasets | P1 | Uploaded sample_logistics 5 rows | analyze_dataset | Analyzes the upload, not an industry template | dataset sample_logistics, 8 columns, row_count 5, quality 90.5 | Pass | TRACK_NO semantic type string
TC-025 | Datasets | P1 | Uploaded sample_retail 5 rows | analyze_dataset | Analyzes the upload | 6 columns, row_count 5, quality 92.0 | Pass | cust_id, order_total, SKU
TC-026 | Datasets | P1 | Uploaded sample_hr 5 rows | analyze_dataset | Analyzes the upload and flags PII | row_count 5, PII full_name and salary_amt | Pass | Names not copied beyond the tool's own sample
TC-027 | Datasets | P1 | Uploaded sample_payments csv 10 rows and tsv 3 rows | analyze_dataset sample_payments | Returns the uploaded file, not Financial Services | Returned dataset Financial Services, row_count 0, synthetic sample_* placeholders | Fail | Production defect. Underscore stem missed, then keyword payment selected the empty finance template. Fixed in services/dataset_resolve.py. Production not redeployed.
TC-028 | Datasets | P1 | Listed uploads scale_100k, mapping_golden, sample_schema_types, sample_mixed_types | analyze_dataset by listed name | Each listed stem resolves | Each returned Dataset not found | Fail | Same resolver. Folded exact match added. Unit tests pass. Production still on the old resolver.
TC-029 | Datasets | P2 | sample_logistics | search_data TRACK_NO | Column hit on the real upload | 1 hit, dataset sample_logistics, match column | Pass | search_data
TC-030 | Datasets | P2 | sample_logistics | profile_quality_rules | Rules cite preflight gates, no invented parse floor | G3/G8/G9 named. honesty: no invented numeric parse-success floor | Pass | profile_quality_rules
TC-031 | Datasets | P2 | sample_logistics vs sample_retail | compare_datasets | Exact column names, case preserved | shared_columns empty. CUST_ID and cust_id stay distinct | Pass | Exact compare is the contract. Not folded.
TC-032 | Datasets | P1 | Resolver unit fixture | pytest tests/test_dataset_name_resolution.py | sample_payments binds the 10-row csv; .tsv binds 3 rows; scale_100k and mapping_golden resolve; payment does not select the empty template; ambiguous email stays unbound | 7 passed | Pass | PYTHONPATH=apps/api
TC-033 | Jobs | P1 | Live job store | list_jobs limit 20 and status census | Page plus whole-history counts | total 575 = failed 388 + completed 180 + cancelled 6 + completed_with_quarantine 1 | Pass | Census arithmetic holds
TC-034 | Jobs | P2 | Completed kilo job | get_job | Completed job does not claim source re-read it did not do | records 10, rejected 0, error null on get_job. List snippet says dest fingerprint matched and source warehouse was not re-read | Pass | Honesty kept. Not marked migration_proven.
TC-035 | Contracts | P2 | list_contracts limit 20 | Returned count | count is the page, not a hidden total | count 20, rows 20 | Pass | Page length. See TC-040 for the brief.
TC-036 | Contracts | P1 | list_contracts limit 200 | Population | Brief's 50 must not be smaller than a fuller read | 200 rows returned, at the tool cap: signed 141, draft 57, deprecated 2 | Fail | Population is at least 200. Brief reported 50 because it listed limit 50 and used the page length as the count.
TC-037 | Schedules | P2 | Live workspace | list_schedules | Empty schedule store is reported empty | schedules [], count 0. Brief schedule_count 0 | Pass | No schedule was created or run
TC-038 | Product honesty | P1 | explain_product CDC exactly once | Answer | CDC default is at-least-once upsert | Answer states at-least-once upsert, idempotent on _df_lsn, not exactly-once | Pass | explain_product
TC-039 | Product honesty | P2 | recommend_sync_mode workload cdc with cursor and pk; inspect add_column | Mode and schema policy | CDC requires log access. Add column is review, not auto-apply | recommended Incremental CDC, requires cdc_log_access. add_column severity review, auto_apply false | Pass | Both tools
TC-040 | Brief | P1 | Same moment as list_jobs | brief job_count vs list_jobs total | One caller sees one job population | Live retest still shows brief 544 and list_jobs total 575 with no scope field. This build defaults list_jobs to scope=workspace (workspace_id ""), and scope=all is explicit. | Fail | Production has not deployed the scope parameter (retest 2026-10-04, total 575, keys count/jobs/status_counts/store/total). Unit test_job_list_scope.py passed: workspace -> "", all -> None.
TC-041 | Brief | P1 | Contract store census | brief contract_count after the code fix | A full page of 50 is replaced by count_contracts_by_status | In-memory fixture of 80 contracts: census returns 80 and 40 unsigned. List page of 50 is not the count | Pass | tests/test_contract_census.py. Production brief stays wrong until this build is deployed.
TC-042 | Mapping | P2 | explain_mapping_assurance | Guarantees | Hungarian assignment, no duplicate targets, fail closed when ambiguous | assignment optimal_bipartite_hungarian. not_claimed: no perfect semantics without ground truth | Pass | No live source/dest pair was mapped. Only PostgresVenkat is up.
TC-043 | Transfer | P1 | Two live connectors and a disposable table | plan_transfer and start_transfer with real rows | Not executed | Blocked. Starting a write against PostgresVenkat would mutate the only live warehouse. 10 of 11 connectors are down. | Blocked | No transfer was started, cancelled, retried, or deleted.
TC-044 | Local matrix | P1 | Postgres, MySQL, Redis on this runner | docs/LIVE_MATRIX_RUNBOOK.md pytest matrix | Engines listening, then the transfer suite | Blocked. No Docker, no database packages, no project virtualenv, fastapi not installed | Blocked | Do not read a skipped matrix as a pass.
TC-045 | UI | P2 | Transfer Studio map and validate | Browser pass on the running web app | Not executed this session | Blocked. API was not booted on this runner. | Blocked | Prior map-banner work is already on the branch. This session did not re-measure CSS.
TC-046 | Capabilities | P2 | get_transfer_capabilities | Honesty fields | transfer_live_count is not the combination grid | transfer_live_count 46, production_sku_sold 90 of 90, customer_handover_sold 35, description says catalog tiles are not transfer-live. live_combinations marks each matrix cell status live (1628 cells) | Pass | The summary text is the honesty line. The per-cell status means the route is in the live matrix, not that this workspace just transferred it.
TC-047 | Jobs | P1 | services.job_list_scope | job_list_workspace_scope | workspace and this map to "". all maps to None. Any other token is refused. | 15 pytest nodes in the operator set passed, including this function. | Pass | tests/test_job_list_scope.py
TC-048 | API keys | P1 | services.api_key_role | resolve and parse role | A blank stored role is editor. An unknown label is viewer. owner is refused at create. | resolve(None¦''¦' ')==editor. superuser==viewer. parse('owner') raises ValueError. | Pass | tests/test_api_key_role.py
TC-049 | MCP | P1 | confirm_ack without a request | confirm_from_tool | ok false and no mutation | Child process loaded the module without the agent runtime. ok is false. Error names ack_id or confirm_action. | Pass | tests/test_mcp_operator_scope.py
TC-050 | MCP | P1 | mcpClientConfig | absolute URL and snippets | https://www.datawrap.io/api/v1/mcp with a Bearer placeholder. No api.datawrap.io. No mcp-bridge. | 3 node tests passed. | Pass | apps/web/src/lib/mcpClientConfig.test.ts
TC-051 | MCP | P1 | Live tools/list | Look for confirm_action | The deployed server exposes confirm_action | 51 tools. create_connector, start_transfer, and create_schedule are present. confirm_action is not, until this build is deployed. | Blocked | Live tools/list 2026-10-04
TC-052 | Connectors | P1 | 11 saved connectors | test_connector on each | Record the dial result. A refused host is not an engine defect. | 1 pass: PostgresVenkat, 10 tables in public. 10 fail: Snowflake account/warehouse/database/schema/role (4), MySQL 2013 lost connection (4), Postgres server closed the connection, Redis connection reset. | Fail | Live retest 2026-10-04. Same hosts as the first census. No connector was deleted.
TC-053 | Schedules | P2 | Live workspace | list_schedules limit 50 | The tool answers. An empty store stays empty. | ok, count 0, names []. No schedule was created or run. | Pass | Live retest 2026-10-04
TC-054 | Datasets | P1 | Live analyze_dataset sample_payments | Name the upload, not the industry template | 10-row sample_payments upload | Production still returns Financial Services, row_count 0. scale_100k and sample_schema_types are still not found. sample_logistics returns the 5-row upload. The resolver fix is in this branch and is not deployed. | Fail | Live retest 2026-10-04. 22 datasets listed, including the uploads.
TC-055 | Transfers | P1 | services.confirmed_transfer | Build a request from a confirm ack | Database stays database. skip_preflight stays false. A file ack keeps kind=file and the upload path. A path outside the upload tree is refused. | 4 tests passed, including /etc/passwd and an xfer_ spill. | Pass | tests/test_confirmed_transfer.py
TC-056 | Transfers | P1 | payments.csv fixture | start_dataset_transfer then read the ack | Ack is start_transfer, source kind file, destination connector kept, mappings produced. A template name is refused. No rows written. | 2 tests passed. Preflight and dest introspect were the warehouse boundary; parse and mapping pipeline were real. | Pass | tests/test_dataset_transfer_stage.py
TC-057 | MCP | P1 | Temporary connector file. test_first off. | create_connector then confirm_action as editor. Confirm the same ack again. | One connector is saved. Replay returns the same connector id and does not write a second row. | Passed. Name qe-mcp-confirm-connector, type postgresql. Store file was the test tmp path. | Pass | tests/test_mcp_confirm_route.py::test_editor_confirm_saves_one_connector_and_replay_does_not_save_another
TC-058 | MCP | P1 | Viewer role, create_connector ack | confirm_action | Refusal. The ack stays unconsumed. No connector row. | Passed. Error names the viewer role. peek consumed is false. Connector list empty. | Pass | tests/test_mcp_confirm_route.py::test_viewer_confirm_of_create_connector_does_not_consume_the_ack
TC-059 | Schedules | P1 | Mappings from run_mapping_pipeline for id, amount. Temporary schedules.json. | confirm_action on a create_schedule ack, then replay. | One enabled schedule. Cron kept. next_run_at set. Replay does not write a second schedule. | Passed. Name qe-mcp-nightly, cron 0 2 * * *, enabled true, one row in the temp store. | Pass | tests/test_mcp_confirm_route.py::test_editor_confirm_creates_one_enabled_schedule_and_replay_keeps_one
TC-060 | Transfers | P1 | payments.csv under a temporary upload root. Engine call recorded. | confirm_action on a start_transfer ack with kind=file and skip_preflight true. | One engine request, kind=file, skip_preflight forced false. Replay does not call the engine again. | Passed. job-qe-file-1, source payments.csv, destination dest-qe.pay. Engine saw the request once. | Pass | tests/test_mcp_confirm_route.py::test_file_ack_confirm_hands_the_upload_to_the_engine_once
TC-061 | Transfers | P1 | CSV sitting beside the upload root, not inside it. | confirm_action | Refusal. Engine is not called. Ack stays spendable. | Passed. Error says the file is outside the upload directory. peek consumed is false. | Pass | tests/test_mcp_confirm_route.py::test_file_ack_outside_the_upload_tree_is_refused_and_stays_spendable
TC-062 | Transfers | P1 | tests/fixtures/sample_payments.csv (10 rows, CUST_ID through DESC) | start_dataset_transfer then confirm_action. Dest introspect and preflight are the warehouse boundary. | Preview rows 10. Confirm hands one kind=file request to the engine, path is the fixture, mappings include CUST_ID and AMT. Replay returns the same job. | Passed. job-payments-1, destination dest-qe.payments_wh. Parse and mapping pipeline were real. No warehouse write. | Pass | tests/test_mcp_confirm_route.py::test_staged_payments_file_confirms_into_one_engine_request
TC-063 | Schedules | P1 | Enabled schedule in a temporary file. Runner call recorded. | confirm_action on a run_schedule ack, then replay. | Runner called once with manual true. Replay returns the same job id and does not call again. | Passed. job-schedule-1. The real runner was not asked to dial a connector. | Pass | tests/test_mcp_confirm_route.py::test_confirm_runs_a_schedule_once
TC-064 | Connectors | P1 | SQLite file under DATAFLOW_SQLITE_ROOT. No host, no password. | draft_is_complete and test_sqlite | A path inside the root is complete and the probe opens it. A path outside the root is refused by both. DuckDB is complete with a file path. Postgres without a host is refused. | Passed. tests/test_pilot_create_connector.py, two new cases, 6 passed in that file. | Pass | tests/test_pilot_create_connector.py
TC-065 | MCP | P1 | tests/fixtures/sample_payments.csv (10 rows) via POST /api/v1/mcp | create_connector sqlite, confirm, start_dataset_transfer, confirm, create_schedule onto a second sqlite file, confirm, run_schedule_now, confirm, replay | payments COUNT is 10. payments_wh COUNT is 10. Replay does not insert again. | Passed in 1 test. Streamable MCP, real preflight, real engine, real schedule runner. Both sqlite files were under a temporary SQLITE_ROOT. No write to PostgresVenkat. | Pass | tests/test_mcp_sqlite_file_transfer.py::test_mcp_loads_sample_payments_into_sqlite
TC-066 | MCP | P1 | tests/fixtures/sample_mixed_types.jsonl (3 rows, mixed offsets) | start_dataset_transfer with no source_timezone, then with source_timezone=Not/AZone | Both calls are refused. The first names created_at and naive wall-clock and tells the operator to pass source_timezone. The second names the unknown zone. No mixed table is created. | Passed. Refusal happened before confirm, so the engine did not write. | Pass | tests/test_mcp_sqlite_file_transfer.py::test_mcp_loads_tsv_json_and_jsonl_then_pauses_and_deletes_the_schedule
TC-067 | Transfers | P1 | sample_payments.tsv (3), sample_hr.json (5), sample_mixed_types.jsonl with source_timezone=UTC | start_dataset_transfer and confirm for each file into one SQLite connector | payments_tsv COUNT 3 and CUST_ID 2001. hr COUNT 5 and emp_id E001. mixed COUNT 3, metadata_json contains us-east, created_at DDL is TIMESTAMPTZ with clocks 12:00:00, 15:30:00, 08:00:00, payload_b64 is BLOB. | Passed. Streamable MCP, real preflight, real engine. SQLite files were under a temporary SQLITE_ROOT. | Pass | tests/test_mcp_sqlite_file_transfer.py::test_mcp_loads_tsv_json_and_jsonl_then_pauses_and_deletes_the_schedule
TC-068 | Schedules | P1 | Schedule qe-mcp-hr-nightly from hr to a second SQLite file | create_schedule, confirm, set_schedule_enabled false, confirm, delete_schedule, confirm, list_schedules | The schedule is enabled, then paused, then gone. list_schedules count is 0. | Passed. Confirm ran each step once against the isolated schedule store. | Pass | tests/test_mcp_sqlite_file_transfer.py::test_mcp_loads_tsv_json_and_jsonl_then_pauses_and_deletes_the_schedule